## Notes & Guidance
Version | 1.2 | 2023-11-01

## Trajectory
London Plan 10 Year Target Period
5 YHLS Period
| 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Year of Trajectory | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Requirement annualised (Target) | 2157 | 2157 | 2157 | 2157 | 2157 | 2157 | 2157 | 2157 | 2157 | 2157 | 2157 | 2157 | 2157 | 2157 | 2157 | 2157 | 2157 | 2157 | 2157
Cumulative Requirement (Target) | 2157 | 4314 | 6471 | 8628 | 10785 | 12942 | 15099 | 17256 | 19413 | 21570 | 23727 | 25884 | 28041 | 30198 | 32355 | 34512 | 36669 | 38826 | 40983
Annual Past Completions | -3: 1863; -2: 1565; -1: 1080
Reporting Year Completions | 0: 1858
Annual Projected Completions |  |  |  |  | 1670 | 1869 | 2648 | 2218 | 3316 | 4332 | 3986 | 4854 | 4391 | 3460 | 2786 | 2115 | 1726 | 1100 | 1100
Cumulative Completions (delivered & projected) | 1863 | 3428 | 4508 | 6366 | 8036 | 9905 | 12553 | 14771 | 18087 | 22419 | 26405 | 31259 | 35650 | 39110 | 41896 | 44011 | 45737 | 46837 | 47937
Completions against annualised target variance | -294 | -592 | -1077 | -299 | -487 | -288 | 491 | 61 | 1159 | 2175 | 1829 | 2697 | 2234 | 1303 | 629 | -42 | -431 | -1057 | -1057
Completions against cumulative requirement variance | -294 | -886 | -1963 | -2262 | -2749 | -3037 | -2546 | -2485 | -1326 | 849 | 2678 | 5375 | 7609 | 8912 | 9541 | 9499 | 9068 | 8011 | 6954
Completions against requirement variance (Sedgefield) | bar: 3 to 14
Trajectory Requirement Balance (starting at 40983) | 39120 | 37555 | 36475 | 34617 | 32947 | 31078 | 28430 | 26212 | 22896 | 18564 | 14578 | 9724 | 5333 | 1873 | -913 | -3028 | -4754 | -5854 | -6954
Adjusted annualised requirement (rolling) | NA | 2451 | 3043 | 4120 | 4419 | 4906 | 5194 | 4703 | 4642 | 3483 | 1308 | -521 | -3218 | -5452 | -6755 | -7384 | -7342 | -6911 | -5854
Note on A7: Ian WEAKE: At present it is proposed that all years, both past and future, are examined against an annualised version of the 2021 London Plan target, equating to 2,157 units. Whilst the 2021 London Plan targets cover the 10 year period between 2019/20 and 2028/29, it has been decided that for the purpose of this exercise that the Council will roll forward the London Plan target in annualised form to cover the latter period of the trajectory, i.e. 2029/30 – 2036/37. If or when better data becomes available this approach may be modified in future trajectories.
Note on A8: Ian WEAKE: Figures here to inform line chart
Note on A9: Ian WEAKE: The totals here should pull from the 'Completions Total' tab. Figures here to inform bar chart.
Note on A10: Ian WEAKE: The total here should pull from the 'Completions Total' tab. Figures here to inform bar chart.
Note on A11: Ian WEAKE: The totals here pull from the 'Projections Summary Table' tab, from the total forecast completions row. Figures here to inform bar chart.
Note on A12: Ian WEAKE: same as rolling completions. Figures here to inform line chart.
Note on A13: Ian WEAKE: Annualised completions against annualised target
Note on A14: Ian WEAKE: Cumulative completions against cumulative requirement. This is a running balance
Note on A15: Ian WEAKE: Annualised target adjusted to account for rolling balance as existed at the end of the previous year. To be consistent with the 5YHLS methodology and the Sedgefield approach need to consider whether any undersupply arising from years 1-3 (1775) must be satisfied over years 4-8 and therefore this component of the undersupply shouldn't be rolled forward past this date (instead along the residual amount accumulated beyond that should be carried forward). Might be worth generating both calculations.
Note on A17: Ian WEAKE: Annualised target adjusted to account for rolling balance as existed at the end of the previous year. To be consistent with the 5YHLS methodology and the Sedgefield approach need to consider whether any undersupply arising from years 1-3 (1775) must be satisfied over years 4-8 and therefore this component of the undersupply shouldn't be rolled forward past this date (instead along the residual amount accumulated beyond that should be carried forward). Might be worth generating both calculations.

## Conventional Comp (small sites)
Scheme level completion data not populated as yet. Revert to aggregated 'Completion Totals' Financial year totals will ultimately feed 'Completions Total' tab.
Financial Year 2019-20 | [25 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Planning Permission No. | Decision | Appeal | Permission Date | Start Date | Completion Date | Site Name / Address | Development Proposal | Units Gained | Units Lost | Net No. Units | Bedrooms (small HMO) | Development Type | Ward | Neighbourhood Area | Easting | Northing | UPRN | Overlaps Adopted Allocation | Overlaps Emerging Allocation | Site Area | Completion Status | Units pending implementation | Total Construction Period | Notes | Year of Trajectory | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Ref | [20 empty] | Fully or Part Completed |  | x years, x months, x days
Total
Financial Year 2020-21 | [25 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Planning Permission No. | Decision | Appeal | Permission Date | Start Date | Completion Date | Site Name / Address | Development Proposal | Units Gained | Units Lost | Net No. Units | Bedrooms (small HMO) | Development Type | Ward | Neighbourhood Area | Easting | Northing | UPRN | Overlaps Adopted Allocation | Overlaps Emerging Allocation | Site Area | Completion Status | Units pending implementation | Construction Period | Notes | Year of Trajectory | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Ref | [20 empty] | Fully or Part Completed |  | x years, x months, x days
Total
Financial Year 2021-22 | [25 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Planning Permission No. | Decision | Appeal | Permission Date | Start Date | Completion Date | Site Name / Address | Development Proposal | Units Gained | Units Lost | Net No. Units | Bedrooms (small HMO) | Development Type | Ward | Neighbourhood Area | Easting | Northing | UPRN | Overlaps Adopted Allocation | Overlaps Emerging Allocation | Site Area | Completion Status | Units pending implementation | Construction Period | Notes | Year of Trajectory | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Ref | [20 empty] | Fully or Part Completed |  | x years, x months, x days
Total
Financial Year 2022-23 | [25 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Planning Permission No. | Decision | Appeal | Permission Date | Start Date | Completion Date | Site Name / Address | Development Proposal | Units Gained | Units Lost | Net No. Units | Bedrooms (small HMO) | Development Type | Ward | Neighbourhood Area | Easting | Northing | UPRN | Overlaps Adopted Allocation | Overlaps Emerging Allocation | Site Area | Completion Status | Units pending implementation | Construction Period | Notes | Year of Trajectory | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Ref | [20 empty] | Fully or Part Completed |  | x years, x months, x days
Total

## Conventional Comp (large sites)
Scheme level completion data not populated as yet. Revert to aggregated 'Completion Totals' Financial year totals will ultimately feed 'Completions Total' tab. | [22 empty] | Note completions data unavailable at present. Dummy data used to illustrate workings only. Financial year totals will ultimately feed 'Completions Total' tab.
Financial Year 2019-20 | [25 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Planning Permission No. | Decision | Appeal | Permission Date | Start Date | Completion Date | Site Name / Address | Development Proposal | Units Gained | Units Lost | Net No. Units | Bedrooms (small HMO) | Development Type | Ward | Neighbourhood Area | Easting | Northing | UPRN | Overlaps Adopted Allocation | Overlaps Emerging Allocation | Site Area | Completion Status | Units pending implementation | Total Construction Period | Notes | Year of Trajectory | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Ref | [20 empty] | Fully or Part Completed |  | x years, x months, x days
Total
Financial Year 2020-21 | [25 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Planning Permission No. | Decision | Appeal | Permission Date | Start Date | Completion Date | Site Name / Address | Development Proposal | Units Gained | Units Lost | Net No. Units | Bedrooms (small HMO) | Development Type | Ward | Neighbourhood Area | Easting | Northing | UPRN | Overlaps Adopted Allocation | Overlaps Emerging Allocation | Site Area | Completion Status | Units pending implementation | Construction Period | Notes | Year of Trajectory | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Ref | [20 empty] | Fully or Part Completed |  | x years, x months, x days
Total
Financial Year 2021-22 | [25 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Planning Permission No. | Decision | Appeal | Permission Date | Start Date | Completion Date | Site Name / Address | Development Proposal | Units Gained | Units Lost | Net No. Units | Bedrooms (small HMO) | Development Type | Ward | Neighbourhood Area | Easting | Northing | UPRN | Overlaps Adopted Allocation | Overlaps Emerging Allocation | Site Area | Completion Status | Units pending implementation | Construction Period | Notes | Year of Trajectory | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Ref | [20 empty] | Fully or Part Completed |  | x years, x months, x days
Total
Financial Year 2022-23 | [25 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Planning Permission No. | Decision | Appeal | Permission Date | Start Date | Completion Date | Site Name / Address | Development Proposal | Units Gained | Units Lost | Net No. Units | Bedrooms (small HMO) | Development Type | Ward | Neighbourhood Area | Easting | Northing | UPRN | Overlaps Adopted Allocation | Overlaps Emerging Allocation | Site Area | Completion Status | Units pending implementation | Construction Period | Notes | Year of Trajectory | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Ref | [20 empty] | Fully or Part Completed |  | x years, x months, x days
Total

## Completions (NSC)
Scheme level completion data not populated as yet. Revert to aggregated 'Completion Totals' Financial year totals will ultimately feed 'Completions Total' tab.
Financial Year 2019-20 | [26 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Planning Permission No. | Decision | Appeal | Permission Date | Start Date | Completion Date | Site Name / Address | Development Proposal | Bedrooms Gained | Bedrooms Lost | Net No. Bedrooms | NSC Type | Unit Net (Converted) | Development Type | Ward | Neighbourhood Area | Easting | Northing | UPRN | Overlaps Adopted Allocation | Overlaps Emerging Allocation | Site Area | Completion Status | Units pending implementation | Total Construction Period | Notes | Year of Trajectory | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Ref | [21 empty] | Fully or Part Completed |  | x years, x months, x days
Total
Financial Year 2020-21 | [26 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Planning Permission No. | Decision | Appeal | Permission Date | Start Date | Completion Date | Site Name / Address | Development Proposal | Bedrooms Gained | Bedrooms Lost | Net No. Bedrooms | NSC Type | Unit Net (Converted) | Development Type | Ward | Neighbourhood Area | Easting | Northing | UPRN | Overlaps Adopted Allocation | Overlaps Emerging Allocation | Site Area |  | Units pending implementation | Construction Period | Notes | Year of Trajectory | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Ref | [21 empty] | Fully or Part Completed |  | x years, x months, x days
Total
Financial Year 2021-22 | [26 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Planning Permission No. | Decision | Appeal | Permission Date | Start Date | Completion Date | Site Name / Address | Development Proposal | Bedrooms Gained | Bedrooms Lost | Net No. Bedrooms | NSC Type | Unit Net (Converted) | Development Type | Ward | Neighbourhood Area | Easting | Northing | UPRN | Overlaps Adopted Allocation | Overlaps Emerging Allocation | Site Area |  | Units pending implementation | Construction Period | Notes | Year of Trajectory | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Ref | [21 empty] | Fully or Part Completed |  | x years, x months, x days
Total
Financial Year 2022-23 | [26 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Planning Permission No. | Decision | Appeal | Permission Date | Start Date | Completion Date | Site Name / Address | Development Proposal | Bedrooms Gained | Bedrooms Lost | Net No. Bedrooms | NSC Type | Unit Net (Converted) | Development Type | Ward | Neighbourhood Area | Easting | Northing | UPRN | Overlaps Adopted Allocation | Overlaps Emerging Allocation | Site Area |  | Units pending implementation | Construction Period | Notes | Year of Trajectory | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Ref | [21 empty] | Fully or Part Completed |  | x years, x months, x days
Total

## Completions Total
Note completions breakdown unavailable at present. Only aggregated totals are known as included below.
| 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Component | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Conventional Completions (Small Sites)
Conventional Completions (Large Sites)
Non Conventional Completions
Completions Total | 1863 | 1565 | 1080 | 1858

## Projections Summary Table
|  | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Status | Component | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Component Total
Pipeline: Extant Permission | Conventional Large |  |  |  |  | 1200 | 1269 | 1959 | 1652 | 2043 | 1735 | 1075 | 730 | 512 | 20 | 0 | 0 | 0 | 0 | 0 | 12195
Pipeline: Extant Permission | Non Conventional (NSC) |  |  |  |  | 0 | 130 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260
Pending: Schemes awaiting decision | Conventional Large |  |  |  |  | 46 | 46 | 135 | 142 | 312 | 366 | 260 | 151 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 1609
Pending: Schemes awaiting decision | Non Conventional (NSC) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 43 | 43 | 43 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 173
Without relevant permission and unimplemented | Site Allocations Conventional Large |  |  |  |  | 0 | 0 | 0 | 0 | 537 | 1589 | 2009 | 3331 | 2870 | 2624 | 1969 | 1297 | 926 | 378 | 378 | 17908
Without relevant permission and unimplemented | Site Allocations Non Conventional |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Without relevant permission and unimplemented | Conventional Large Windfall Masterplan |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 175 | 175 | 175 | 390 | 392 | 393 | 394 | 376 | 298 | 298 | 3066
Forecast/Modelled | Conventional Small Sites | 0 | 0 | 0 | 0 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 6360
Totals | bar: 1 to 15
_ | Conventional Large forecast completions | 0 | 0 | 0 | 0 | 1246 | 1315 | 2094 | 1794 | 2892 | 3865 | 3519 | 4387 | 3923 | 3036 | 2362 | 1691 | 1302 | 676 | 676 | 34778
_ | Non Conventional forecast completions | 0 | 0 | 0 | 0 | 0 | 130 | 130 | 0 | 0 | 43 | 43 | 43 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 433
_ | Conventional Small Sites forecast completions | 0 | 0 | 0 | 0 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 6360
_ | Total forecast completions | 0 | 0 | 0 | 0 | 1670 | 1869 | 2648 | 2218 | 3316 | 4332 | 3986 | 4854 | 4391 | 3460 | 2786 | 2115 | 1726 | 1100 | 1100 | 41571
Note on B4: Ian WEAKE: These figures derive from the conventional large pipeline tab.
Note on B5: Ian WEAKE: These figures pull from the NSC Pipeline tab. NSC pipeline should include large and small sites
Note on B6: Ian WEAKE: These derive from the Conventional pending tab.
Note on B7: Ian WEAKE: From the NSC pending tab. As per 2017 SHLAA methodology - see para 7.13
Note on B8: Ian WEAKE: From conventional allocations large
Note on B9: Ian WEAKE: From NSC Allocations tab. The inclusion of NSC from allocations is consistent with SHLAA methodology (see para 7.13). Should include small and large sites as per SHLAA (see para. 7.15)
Note on B11: Ian WEAKE: 7.15 NSC accommodation is not included in the assessment of capacity on small sites, which is based on completions trends for ‘conventional’ self-contained housing (Use Class C3), alongside modelling which examines the scope to increase these trends, taking into account the small sites policy in the London Plan.
Note on B13: Ian WEAKE: Total of large pipeline, large pending and large allocations.
Note on B14: Ian WEAKE: Total of NSC pipeline, NSC pending and Site Allocations Non Conventional.
Note on B15: Ian WEAKE: Small Sites forecasts are based on conventional supply only. NSC accommodation is not included in the assessment of capacity on small sites, which is based on completions trends for ‘conventional’ self-contained housing (Use Class C3), alongside modelling which examines the scope to increase these trends, taking into account the small sites policy in the London Plan.

## Conventional Pipeline (Large)
[7 empty] | Unimplemented Units | [18 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Planning Permission No. | Decision | Appeal | Permission Date | Start Date | Site Name / Address | Development Proposal | Units Gained | Units Lost | Net No. Units | Bedrooms (small HMO) | Development Type | Ward | Neighbourhood Area | Easting | Northing | UPRN | Overlaps Adopted Allocation | Overlaps Emerging Allocation | Unimplemented Capacity Substituted by Allocation | Site Area | Net Capacity to plug into Trajectory | Scheme Progress | Notes | Phasing Notes | Year of Trajectory | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Scheme Total
223203FUL | Grant with S106 Obligations |  | 2023-02-09 | 2023-03-22 | The Steyne Estate, Steyne Road, W3 9NF |  | 188 | 0 | 188 |  |  | South Acton | Acton |  |  |  | No | Allocation (AC02) not pursued | 0 | 1.42 | 188 | Started |  | CIL records confirm commencement late March 2023. Bespoke - Phasing informed by scheme specific information - Anticipate delivery within years 6 - 8. | [5 empty] | 0 | 0 | 94 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188
182579OUT | Grant with S106 Obligations |  | 2018-12-24 |  | Acton Gardens (Phases 7-11) |  | 1950 | ? | ? |  |  | South Acton | Acton |  |  |  | No | AC04 | 1747 (gross) |  | 0 | Part Completed Part Superseded |  | NA | [20 empty] | 0 | bar: 1 to 15
215892REM | Grant with Conditions |  | 2021-12-24 |  | Acton Gardens (Phases 9.3, 9.5 & 9.6) |  | 215 |  |  |  |  | South Acton | Acton |  |  |  | No | AC04 | 215 |  | 0 | Approval |  | NA | [20 empty] | 0 | bar: 1 to 15
221747HYBRID | Grant with S106 Obligations |  | 2023-05-03 | 2021-03-01 | Friary Park Estate, The Drive, Joseph Avenue, Sparks Close and Friary Road, Acton W3 6NL | Superseded 193424HYBRID | 1228 | 230 | 998 |  |  | East Acton | Acton |  |  |  | No | Allocation (AC11) not pursued | 0 | 2.83 | 998 | Started |  | Bespoke - Phasing informed by scheme specific information - Although works have started on site, given the scale of scheme it is not considered likely that all units will be completed within 5 years. Phasing plan indicates site to be constructed in 3 phases over a period of 7 years - phase 3 earliest completion date is anticipated to be Q3 2028. Phase 1 (circa 530net): Commence Q1 2021 - Complete Q4 2025. Phase 2: Commence Q1 2023 - Complete Q1 2025. Phase 3: Commence Q3 2025 - Complete Q3 2028. | [5 empty] | 100 | 265 | 265 | 0 | 184 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 998
224371FUL | Grant with S106 Obligations |  | 2023-09-13 |  | Land Between Park View And Cloister Road Western Avenue Acton London W3 6XZ |  | 300 | 0 | 300 |  |  | North Acton | Acton |  |  |  | OIS3 | No | NA | 0.82 | 300 | Approval |  | Scenario 10 | [5 empty] | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300
201379OUT | Grant with S106 Obligations |  | 2021-12-22 |  | TfL Landholdings At Bollo Lane Acton Ealing Bounded By The Railway Lines To The West Acton Town Station To The North Bollo Lane To The East And The Bollo Lane Level Crossing To The South. London W3 8QU | Hybrid Application - Phases 1 & 2 in full (195 units), Phases 3 & 4 in outline (657 units) | 852 | 0 | 852 |  |  | South Acton | Acton |  |  |  | No | South Acton LSIS Windfall | NA | 3.64 | 852 | Approval |  | Bespoke - Phasing informed by hybrid status of permission | [5 empty] | 0 | 0 | 0 | 170 | 170 | 170 | 171 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 852
193500FUL | Grant with S106 Obligations |  | 2021-09-08 |  | 72-76 Broadway West Ealing London W13 0SY |  | 56 | 0 | 56 |  |  | Hanwell Broadway | Ealing |  |  |  | EA15 | EA16 | 56 | 0.18 | 0 | Approval |  | NA | [20 empty] | 0 | bar: 1 to 15
P/2015/0072 | Grant with S106 Obligations |  | 2015-11-19 | TBC | Green Man Lane | Need to confirm whether anything is outstanding. Phases 1, 2, 3 & 5 completed under P/2010/0419. This permission also encompassed a replacement school alongside residential units Phase 6a and part of 6b were under construction when last reported. | 92 | 0 | 92 |  |  | Hanwell Broadway | Ealing |  |  |  | No | Allocation (Reg 18 EA23) not pursued | 53 | 1.75 | 39 | Started |  | Scenario 3 |  | 1: 19; 2: 20 | 39
P/2015/4089 | Grant with S106 Obligations |  | 2017-02-20 | 2020-02-14 | Castle House & Rome House 119 - 127 Gordon Road West Ealing W13 8QD |  | 172 | 0 | 172 |  |  | Ealing Broadway | Ealing |  |  |  | EAL13 | EA26 | 172 | 1.46 | 0 | Part Lapsed (Phase 2) |  | NA | [20 empty] | 0 | bar: 1 to 15
222341FUL | Grant with S106 Obligations |  | 2023-02-09 |  | Twyford Abbey Nursing Home Twyford Abbey Road Park Royal London NW10 7DP |  | 326 | 0 | 326 |  |  | Hanger Hill | Ealing |  |  |  | No | EA30 | 0 | 5.4 | 326 | Approval |  | Bespoke - Phasing informed by scheme specific information - Although works have yet to start on site applicant is actively discharging pre-commencement conditions which signals that works may commence shortly. Site is to be developed in phases. It is assumed that some units might be delivered from year 4 (trajectory year 7) onwards. Assume completion by or before year 10. | [5 empty] | 0 | 0 | 81 | 81 | 82 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326
203719FUL | Grant with S106 Obligations |  | 2021-02-03 | 2023-01-04 | Maitland Yard And Dean Gardens Car Parks, W13 9AN |  | 53 | 0 | 53 |  |  | Walpole | Ealing |  |  |  | EAL14 | No | NA | 0.42 | 53 | Started |  | Bespoke - Phasing informed by scheme specific information. Completion could be possible within first 5 years, but note works have stalled recently. | [5 empty] | 0 | 27 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53
P/2014/6383 | Grant with S106 Obligations |  | 2015-10-23 | TBC | Sherwood Close (Phase 2 Blocks B7 & B8) | Part superseded by 178303VAR | 49 |  | 49 |  |  | Walpole | Ealing |  |  |  | No | No | 0 |  | 49 | Started |  | Bespoke - Blocks B7 and B8 still under construction as of September 2022. BC records indicate that works completed in August 2023 (i.e. within future year 23/24). | [5 empty] | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49
212893FUL | Grant with S106 Obligations |  | 2022-07-13 |  | 1 Pitshanger Lane Ealing London W5 1RH |  | 60 | 38 | 22 |  |  | Pitshanger | Ealing |  |  |  | No | No | NA | 0.25 | 22 | Approval |  | Scenario 8 | [5 empty] | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
171721FUL | Grant with S106 Obligations |  | 2018-02-02 | 2020-10-08 | Orion Park Northfield Avenue West Ealing W13 9SJ | Part superseded by 213744VAR | 76 | 0 | 76 |  |  | Northfield | Ealing |  |  |  | No | No | NA | 0.65 | 76 | Started |  | Bespoke. CIL records confirm commencement in October 2020, but apart from site clearance progress is slow | [5 empty] | 0 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76
213744VAR | Grant with S106 Obligations |  | 2021-12-08 | 2020-10-08 | Orion Park Northfield Avenue West Ealing W13 9SJ | Part supersedes 171721FUL adding a further 19 units | 19 | 0 | 19 |  |  | Northfield | Ealing |  |  |  | No | No | NA | 0.65 | 19 | Started |  | Bespoke. CIL records confirm commencement in October 2020 of parent application, but apart from site clearance progress is slow | [5 empty] | 0 | 0 | 9 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
182843FUL | Grant with S106 Obligations |  | 2020-01-10 | TBC | Kellogg Tower Greenford Road Greenford Middlesex UB6 0JA (Car Park and Building 1) |  | 270 | 0 | 270 |  | New Build | North Greenford | Greenford |  |  |  | No | No | NA | 2.37 | 270 | Started |  | Works have commenced. Scenario 5 | [5 empty] | 67 | 67 | 68 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270
164694FUL | Grant with S106 Obligations |  | 2017-09-01 | 2018-07-01 | Former GlaxoSmithKline Site And Former Sunblest Bakery Site Greenford Road Greenford UB6 0HE | Part superseded by 18488VAR | 1088 | 0 | 1088 |  |  | Central Greenford | Greenford |  |  |  | OIS7 | No | NA | TBC | 1088 | Started |  | Started July 2018. Blocks 3, 4 (part against this permission and part against 184888VAR) and 5 have been completed. Blocks 6 & 8 are next in the phasing strategy. Scenario 6. | [5 empty] | 217 | 217 | 218 | 218 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088
184888VAR | Grant with S106 Obligations |  | 2020-01-10 |  | Former GlaxoSmithKline Site And Former Sunblest Bakery Site Greenford Road Greenford UB6 0HE | Amends blocks 4, 5, 6, 7 & 8 | 122 | 0 | 122 |  |  | Central Greenford | Greenford |  |  |  | OIS7 | No | NA | TBC | 122 | Started |  | Block 4 completed August 2022. Blocks 6 & 8 were next in the phasing strategy. Align with phasing for main original applictioan - i.e. Scenario 6 | [5 empty] | 24 | 24 | 24 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122
203713FUL | Grant with S106 Obligations |  | 2021-02-03 | 2021-11-29 | Land Adjacent To 5 - 17 Chesterton Close And 5 - 17 Evesham Close Greenford UB6 9TE |  | 25 | 0 | 25 |  |  | Greenford Broadway | Greenford |  |  |  | No | No | NA | 0.59 | 25 | Started |  | CIL records confirm works commenced November 2021. Scenario 3 | [5 empty] | 12 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
214662OUT | Grant with S106 Obligations |  | 2022-10-27 |  | The Transport Yard Wood End Gardens Northolt Middlesex UB5 4QH | Outline permission | 149 | 0 | 149 |  |  | North Greenford | Greenford |  |  |  | No | No | NA | 0.59 | 149 | Approval |  | Scenario 14 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 49 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149
PP/2013/2127 | Grant with S106 Obligations |  | 2013-10-23 |  | Copley Close, W7 1QG | Part superseded by 172235FUL & 184111NMA (phase 6) | 16 | 14 | 2 |  |  | Pitshanger | Hanwell |  |  |  | OIS6 | HA12 | 2 |  | 0 | Started (with exception of phase 7) |  | NA | [20 empty] | 0 | bar: 1 to 15
210009OUT | Grant with S106 Obligations |  | 2023-03-22 | 2023-05-09 | High Lane Estate Hobbayne Road Hanwell W7 3RJ | Hybrid Application. Phase 1 in full. Phases 2 & 3 in outline. | 505 | 264 | 241 |  |  | North Hanwell | Hanwell |  |  |  | No | HA13 | 0 | 3.52 | 241 | Started |  | Bespoke - Phasing informed by scheme specific information. Work has started on block K (shop) in May 2023.Have to deliver in a linear fashion - limited space for decanting. Phase 1 must be completed . Hope to reach practical completion on phase 1 within 2.5 years. Only then can phase 2 start - build out over next 2.5 years . Then phase 3 within next 2.5 years. 7.5 years - 10 years total build out - but timing ultimately subject to funding and so may be some slippage. | [5 empty] | 0 | 0 | 72 | 0 | 0 | 94 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 241
P/2012/5040 | Grant with Conditions |  | 2013-07-22 |  | St Bernard's Hospital Uxbridge Road Southall Middlesex UB1 3HW |  | 214 | 0 | 214 |  |  | Norwood Green | Hanwell |  |  |  | No | No | 0 |  | 214 | Started |  | Phase S3, comprising the remaining 214 residential units would commence later due to the Trust’s need to maintain services during the construction of the new Medium Secure Unit. Scenario 14. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 71 | 71 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214
177284FUL | Grant with S106 Obligations |  | 2018-09-06 | TBC | Wickes & Nissan, 75-117 Boston Road Hanwell London W7 3SA | Part superseded by 191309FUL & 210104VAR | 169 | 0 | 169 |  |  | Hanwell Broadway | Hanwell |  |  |  | HAN3 | No | 0 | 1.45 | 169 | Started |  | Bespoke. Phasing informed by scheme specific information. Phase 2 due to complete Summer 2024 | [5 empty] | 0 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169
184014FUL | Grant with S106 Obligations |  | 2020-07-31 | 2021-06-21 | 4 Trumpers Way Hanwell London W7 2QA (Elthorne Works) | Part superseded by 233548NMA (adjusts tenure mix only) | 213 | 0 | 213 |  |  | Hanwell Broadway | Hanwell |  |  |  | No | No | 0 | 1.08 | 213 | Started |  | Bespoke. CIL records confirm commencment June 2021, although not advanced beyond site clearance. Recent NMA application. | [5 empty] | 0 | 0 | 71 | 71 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213
220545FULR3 | Grant with S106 Obligations |  | 2023-05-23 |  | Site Of Former Northolt Grange Community Centre And Part Of St Raphael's Catholic School Northolt Middlesex UB5 6NF | See also 213792HYBRID (no resi. Component) | 92 | 0 | 92 |  | New Build | Northolt West End | Northolt |  |  |  | No | Allocation (Reg 18 NO14) not pursued | 0 | 0.61 | 92 | Approval |  | Bespoke. Pre-commencement conditions are currently being discharged suggesting commencement shortly. | [5 empty] | 0 | 46 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92
194996FUL | Grant with S106 Obligations |  | 2020-10-02 | 2021-03-01 | Land At Dabb's Hill (West Of Perth And Huntingdon Close) Northolt Middlesex UB5 4AX | Part superseded by 221262NMA (adjusts tenure mix only) | 149 | 0 | 149 |  | New Build | Northolt Mandeville | Northolt |  |  |  | No | No | NA | 1.28 | 149 | Started |  | Bespoke. Within 5 years. | [5 empty] | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149
200534FUL | Grant with S106 Obligations |  | 2021-02-12 | 2021-05-11 | Land Rear Of Tesco Superstore Hoover Building Western Avenue Perivale UB6 8DW |  | 278 | 0 | 278 |  | New Build | Perivale | Perivale |  |  |  | No | No | NA | 1.9 | 278 | Started |  | Bespoke. Phasing informed by scheme specific information. Works commenced May 2021. Now well advanced. Due to complete early 2024. | [5 empty] | 278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278
216991FULR3 | Grant with S106 Obligations |  | 2023-03-02 | 2023-05-29 | Land South Of Park Avenue Park Avenue Southall Middlesex UB1 3AD | Part superseded by 232654VAR (pending but doesn't alter unit totals) | 516 | 23 | 493 |  | New Build | Southall Broadway | Southall |  |  |  | SOU4 | Allocation (Reg 18 SO02) not pursued | NA | 1.24 | 493 | Started |  | CIL records confirm commencement May 2023 for phase 1. 3 phases proposed in total. Scenario 6 (reflecting gross total) | [5 empty] | 98 | 98 | 99 | 99 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493
201888FUL | Grant with S106 Obligations |  | 2022-01-19 | 2023-05-04 | Southall Sidings Park Avenue Southall Middlesex UB1 3AD |  | 460 | 0 | 460 |  |  | Southall Broadway | Southall |  |  |  | SOU4 | SO03 | 0 | 1.16 | 460 | Started |  | Bespoke. Phasing informed by scheme specific information. CIL records confirm commencement May 2023. Although progressing revisions are anticipated for phase B. | [5 empty] | 0 | 0 | 115 | 115 | 115 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460
PP/2015/4921 | Grant with S106 Obligations |  | 2017-02-17 | 2020-01-28 | 96 South Road Southall Middlesex UB1 1RB | Part superseded by 222363VAR (amends PP/2015/4921 but doesn't alter unit totals) | 41 | 0 | 41 |  |  | Southall Broadway | Southall |  |  |  | SOU3 | SO04 | 41 | 0.32 | 0 | Started |  | CIL records confirm commencement January 2020 | [20 empty] | 0 | bar: 1 to 15
203705FUL | Grant with S106 Obligations |  | 2021-05-12 | 2022-10-19 | Former Southall College Site Beaconsfield Road Southall UB1 1DP | Part superseded by 220456VAR (adjusts tenure mix only) | 118 | 0 | 118 |  |  | Southall Broadway | Southall |  |  |  | SOU3 | No (SO05 amended to exclude this site) | NA | 0.38 | 118 | Started |  | CIL records confirm commencement October 2022. Scenario 4 | [5 empty] | 39 | 39 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118
181380FUL | Grant with S106 Obligations |  | 2021-12-22 | 2022-10-07 | The Arches Business Centre Merrick Road Southall UB2 4AU |  | 575 | 0 | 575 |  |  | Norwood Green | Southall |  |  |  | SOU6 | Allocation (Reg 18 SO09) not pursued | NA | 0.64 | 575 | Started |  | Bespoke. CIL records confirm commencement 07/10/2022. | [5 empty] | 0 | 115 | 115 | 115 | 115 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 575
183673OUT | Grant with S106 Obligations |  | 2019-11-29 |  | Middlesex Business Centre Bridge Road Southall Middlesex UB2 4AB | See also reserved matter application 224785REM for plots A & B | 2083 | 0 | 2083 |  |  | Norwood Green | Southall |  |  |  | SOU6 | SO11 | 0 | 4.82 | 2083 | Approval |  | Bespoke. Pending Reserved Matter application is indicative that works may commence within the next 5 years. | [5 empty] | 0 | 0 | 0 | 0 | 416 | 416 | 417 | 417 | 417 | 0 | 0 | 0 | 0 | 0 | 0 | 2083
PP/2013/3241 | Grant with S106 Obligations |  | 2015-04-24 | 2015-07-01 | Phases 1-4, Havelock Estate | Outline permission for all phases | 635 | 536 | 99 |  |  | Norwood Green | Southall |  |  |  | SOU7 | S012 | 0 | 18.3 | 99 | Started |  | Bespoke. Phase 2-4 are subject to an outline permission only at this stage. Whilst it is anticipated that a revised scheme will be submitted for phases 2-4 the timing of this is unclear at present. Phasing should be informed by gross figures in this instance. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 19 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 99
215058FULR3 | Grant with S106 Obligations |  | 2022-09-09 |  | Land Comprising Public Car Park, Business Premises, Roads And Adjacent Land Lying To The North West And Rear Of The Green And Adjoining Featherstone Terrace, Dominion Road And Dilloway Yard, Southall, UB2 (The Green) |  | 564 | 0 | 564 |  |  | Southall Green | Southall |  |  |  | SOU8 | SO13 | 0 | 1.97 | 564 |  |  | 3 blocks. Scenario 11 | [5 empty] | 0 | 0 | 112 | 113 | 113 | 113 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564
185158REM | Grant with Conditions |  | 2019-02-22 |  | Southall Gas Works Site The Straight Southall Middlesex UB1 1QX | Phase 2 | 897 | 0 | 897 |  |  | Southall West | Southall |  |  |  | SOU5 | SO14 | 0 | 6.12 | 897 | Approval |  | Bespoke. As of March 2023 phase 2 has yet to commence. | [5 empty] | 0 | 0 | 179 | 179 | 179 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 897
201123NMA | Approved |  | 2020-04-07 |  | The Straight Southall Middlesex UB1 1QX | Phase 2 | 11 | 0 | 11 |  |  | Southall West | Southall |  |  |  | SOU5 | SO14 | 0 | 6.12 | 11 | Approval |  | Bespoke. As of March 2023 phase 2 has yet to commence. | [5 empty] | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
216077REM | Grant subject to Unilateral Undertaking |  | 2022-08-30 |  | The Straight Southall Middlesex UB1 1QX | Phase 2 | 250 | 0 | 250 |  |  | Southall West | Southall |  |  |  | SOU5 | SO14 | 0 | 6.12 | 250 | Approval |  | Bespoke. As of March 2023 phase 2 has yet to commence. | [5 empty] | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250
205101REM | Grant with S106 Obligations |  | 2021-04-23 | TBC | The Straight Southall Middlesex UB1 1QX | Phase 3 | 645 | 0 | 645 |  |  | Southall West | Southall |  |  |  | SOU5 | SO14 | 0 | 1.95 | 645 | Started |  | Phase 3 is under construction. Scenario 6. | [5 empty] | 129 | 129 | 129 | 129 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 645
190140FUL | Grant with Conditions |  | 2020-06-12 |  | Endsleigh Industrial Estate Endsleigh Road Southall Middlesex UB2 5QR |  | 9 | 0 | 9 |  |  | Norwood Green | Southall |  |  |  | No | SO16 | 0 (50 from wider site) | 0.03 | 9 | ? |  | Phasing assumes that this permission will be implemented independent of allocation, but ultimately may progressed as comprehensive scheme. | [5 empty] | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
221501REM | Grant with S106 Obligations |  | 2022-11-17 | 2023-05-30 | Alnmouth & Portrush Court | Phase 3 | 143 | 84 | 59 |  |  | Dormers Wells | Southall |  |  |  | No | SO23 (unless amended to exclude phase 3) | 0 | 0.77 | 59 | Started |  | Phase 3 is under construction commencing in March 2023. Scenario 4 (reflecting gross total). | [5 empty] | 19 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59
[25 empty] | Total |  |  |  |  | 1200 | 1269 | 1959 | 1652 | 2043 | 1735 | 1075 | 730 | 512 | 20 | 0 | 0 | 0 | 0 | 0 | 12195
0
0
0
0
0
0
0
0
0
[46 empty] | Acton | 2338
[46 empty] | Ealing | 584
[46 empty] | Greenford | 1654
[46 empty] | Hanwell | 837
[46 empty] | Northolt | 241
[46 empty] | Perivale | 278
[46 empty] | Southall | 6263

## NSC Pipeline
[7 empty] | Unimplemented bedrooms | [21 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Planning Permission No. | Decision | Appeal | Permission Date | Start Date | Site Name / Address | Development Proposal | Bedrooms Gained | Bedrooms Lost | Net No. Bedrooms | NSC Type | Unit (C3) lost | Unit Gross (Converted) | Unit Net (Converted) | Development Type | Ward | Neighbourhood Area | Easting | Northing | UPRN | Overlaps Adopted Allocation | Overlaps Emerging Allocation | Unimplemented Capacity Substituted by Allocation | Site Area | Net Capacity to plug into Trajectory | Scheme Progress | Notes | Phasing Notes | Year of Trajectory | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Scheme Total
174485FUL | Grant with S106 obligations |  | 2019-11-26 | Estimated October 2020 | Hanger Lane Gyratory, Hanger Lane, W5 1DL |  | 650 | 0 | 650 | Student (2.5:1) | 0 | 260 | 260 | New build | Hanger Hill | Ealing |  |  |  | No | No | 0 | 0.41 | 260 | Commenced | The permission allows for up to 650 bedrooms, although current designs include 565 bedrooms. Assume completion within first 5 years. Bespoke phasing - | Bespoke phasing - spread over 2 years, although as single block the scheme will likely complete in a single year | [5 empty] | 0 | 130 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260
[28 empty] | Total |  |  |  |  | 0 | 130 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
[48 empty] | 0 | Ealing | 260
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Conventional Pending (Large)
[8 empty] | Proposed Units | [18 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Site or Scheme ID | Planning Permission No. | Decision | Appeal | Permission Date | Start Date | Site Name / Address | Development Proposal | Units Gained | Units Lost | Net No. Units | Bedrooms (small HMO) | Development Type | Ward | Neighbourhood Area | Easting | Northing | UPRN | Overlaps Adopted Allocation | Overlaps Emerging Allocation | Capacity Substituted by Allocation | Site Area | Net Capacity to plug into Trajectory | Application Progress | Notes | Phasing Notes | Year of Trajectory | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Scheme Total
1 |  | lock | lock | lock | lock |  |  | 185 | 0 | 185 |  | New Build | North Acton | Acton | [5 empty] | NA | 0.64 | 185 | Resolution to grant pending legal agreement |  | Bespoke - spread over 3 years | [5 empty] | 0 | 0 | 0 | 0 | 62 | 62 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185
2 |  | lock | lock | lock | lock |  |  | 0 | 4 | -4 |  |  | Ealing Broadway | Ealing | [7 empty] | -4 | Decision not yet taken |  | Likely beyond 5 years | [5 empty] | 0 | 0 | 0 | 0 | 0 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4
3 |  | lock | lock | lock | lock |  |  | 396 | 129 | 267 |  |  | Hanwell Broadway | Ealing | [5 empty] | NA | 1.58 | 267 | Resolution to grant pending legal agreement |  | Bespoke - Phasing informed by scheme specific information. Supporting documents indicate that Phase 4 & 6b estimated to be completed by March 2027 | [5 empty] | 0 | 0 | 89 | 89 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267
4 |  | lock | lock | lock | lock |  |  | 428 | 0 | 428 |  |  | Hanwell Broadway | Ealing | [5 empty] | Yes (all) | 1.68 | 0 | Decision not yet taken |  | NA
5 |  | lock | lock | lock | lock |  |  | 185 | 47 | 138 |  | New Build | Walpole | Ealing | [5 empty] | NA | 0.53 | 138 | Decision not yet taken |  | Bespoke - Phasing informed by scheme specific information. Supporting documents indicate that phase 3 (final phase) should be completed by 2025 | [5 empty] | 46 | 46 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138
6 |  | lock | lock | lock | lock |  |  | 326 | 10 | 316 |  |  | Hanger Hill | Ealing | [5 empty] | NA | 0.78 | 316 | Resolution to grant pending legal agreement |  | Scenario 15 |  | 6: 79; 7: 79; 8: 79; 9: 79 | 316
7 |  | lock | lock | lock | lock |  |  | 36 | 0 | 36 |  | New Build | Greenford Broadway | Greenford | [5 empty] | 36 | 0.13 | 0 | Decision not yet taken |  | NA | [20 empty] | 0 | bar: 1 to 15
8 |  | lock | lock | lock | lock |  |  | 220 | 3 | 217 |  |  | Greenford Broadway | Greenford | [5 empty] | 0 | 1.5 | 217 | Resolution to grant pending legal agreement |  | Planning submission indicates that scheme to be built in 3 phases. Phase 1 indicative completion is June 2026. Phase 2 indicative completion is June 2027. Phase 3 completion by May 2027. As decision is still pending - phasing to be pushed back by one year. | [5 empty] | 0 | 0 | 0 | 0 | 108 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217
9 |  | lock | lock | lock | lock |  |  | 288 | 0 | 288 |  | New Build | North Greenford | Greenford | [5 empty] | NA | 2.37 | 288 | Resolution to grant pending legal agreement |  | Scenario 15, although recognised that implementation may in part run concurrently with 182843FUL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 72 | 72 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 288
10 |  | lock | lock | lock | lock |  |  | 43 | 0 | 43 |  |  | Hanwell Broadway | Hanwell | [5 empty] | 43 | 0.14 | 0 | Resolution to grant pending legal agreement |  | NA | [20 empty] | 0 | bar: 1 to 15
11 |  | lock | lock | lock | lock |  |  | 106 | 0 | 106 |  | New Build | Northolt Mandeville | Northolt | [5 empty] | 0 | 1.7 | 106 | Decision not yet taken |  | Bespoke - Phasing informed by scheme specific information. Application is still pending. Indicative programme suggests works could start in mid 2024. Build out over 2 years. | [5 empty] | 0 | 0 | 0 | 53 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106
12 |  | lock | lock | lock | lock |  |  | 96 | 0 | 96 |  |  | Southall Green | Southall | [5 empty] | 96 | 0.08 | 96 | Resolution to grant pending legal agreement |  | Applicant has indicated a 2 year build out period. Scenario 18 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96
13 |  | lock | lock | lock | lock |  |  | 215 | 0 | 215 |  |  | Southall Green | Southall | [5 empty] | 215 | 0.35 | 0 | Decision not yet taken |  | NA | [20 empty] | 0 | bar: 1 to 15
[26 empty] | Total |  |  |  |  | 46 | 46 | 135 | 142 | 312 | 366 | 260 | 151 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 1609
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[47 empty] | Acton | 185
[47 empty] | Ealing | 717
[47 empty] | Greenford | 505
[47 empty] | Hanwell | 0
[47 empty] | Northolt | 106
[47 empty] | Perivale | 0
[47 empty] | Southall | 96

## NSC Pending
[8 empty] | Proposed Bedrooms | [21 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Site or Scheme ID | Planning Permission No. | Decision | Appeal | Permission Date | Start Date | Site Name / Address | Development Proposal | Bedrooms Gained | Bedrooms Lost | Net No. Bedrooms | NSC Type | Unit (C3) lost | Unit Gross (Converted) | Unit Net (Converted) | Development Type | Ward | Neighbourhood Area | Easting | Northing | UPRN | Overlaps Adopted Allocation | Overlaps Emerging Allocation | Unimplemented Capacity Substituted by Allocation | Site Area | Net Capacity to plug into Trajectory | Application Progress | Notes | Phasing Notes | Year of Trajectory | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Scheme Total
1 |  | lock | lock | lock | lock |  |  | 318 | 0 | 318 | Other (1.8:1) | 4 | 177 | 173 |  | Ealing Broadway | Ealing | [5 empty] | 0 | 0.39 | 173 | Resolution to grant pending legal agreement |  | Scenario 15 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 43 | 43 | 43 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 173
2 |  | lock | lock | lock | lock |  |  | 448 | 0 | 448 | Student (2.5:1) | 0 | 179 | 179 |  | Walpole | Ealing | [5 empty] | 179 | 0.16 | 0 | Decision not yet taken |  | NA |  | 1: 0 | 0
[29 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 43 | 43 | 43 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 173
0 | bar: -3 to -1
0
[49 empty] | 0 | Acton | 0
[49 empty] | 0 | Ealing | 173
[49 empty] | 0 | Greenford | 0
[49 empty] | 0 | Hanwell | 0
[49 empty] | 0 | Northolt | 0
[49 empty] | 0 | Perivale | 0
[49 empty] | 0 | Southall | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on Y4: Ian WEAKE: Unlike conventional for NSC both large and small sites are included

## ConventionalAllocations (Large)
|  |  |  | Unimplemented Capacity | [16 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Site or Scheme ID | Site Allocation Ref. | Site Name / Address | Proposed Use | Estimated Capacity Gross | Estimated Capacity Net | Existing Units Lost | Overlapping Planning Permission | Net Capacity already assigned to pipeline or pending tabs | Remaining Capacity (Net) not assigned to pipeline or pending tabs | Ward | Neighbourhood Area | Easting | Northing | UPRN | Covered by existing Adopted Allocation | Site Area (ha) | Notes | Net Capacity to plug into Trajectory | Phasing Notes | Year of Trajectory | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Scheme Total
1 |  |  |  | 377 | 377 | 0 |  | 0 | 377 | South Acton | Acton |  |  |  |  | 1.3 |  | 377 | Scenario 30. Beyond 5 years | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 75 | 76 | 76 | 0 | 0 | 0 | 377
2 |  |  |  | 188 | 188 | 0 |  | 188 | 0 | South Acton | Acton |  |  |  |  | 1.34 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  |  |  | 262 | 259 | 3 |  | 0 | 259 | South Acton | Acton |  |  |  |  | 0.68 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  |  |  | 3014 | 2054 | 960 |  | 0 | 2054 | South Acton | Acton |  |  |  |  | 10.09 |  | 2054 | Bespoke - Feasibility Study undertaken but revised masterplan application yet to be submitted. Timing of build out should have regard to the gross figures | [5 empty] | 0 | 0 | 0 | 0 | 342 | 342 | 342 | 342 | 343 | 343 | 0 | 0 | 0 | 0 | 0 | 2054
5 |  |  |  | 43 | 43 | 0 |  | 0 | 43 | South Acton | Acton |  |  |  |  | 0.14 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  |  |  | 225 | 225 | 0 |  | 0 | 225 | South Acton | Acton |  |  |  |  | 2.2 |  | 225 | Bespoke - Phasing likely to be informed by scheme specific information. Build out 8-11 years. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 56 | 56 | 57 | 0 | 0 | 0 | 0 | 225
7 |  |  |  | 40 | 40 | 0 |  | 40 | 0 | South Acton | Acton |  |  |  |  | 0.24 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  |  |  | 109 | 63 | 46 |  | 0 | 63 | South Acton | Acton |  |  |  |  | 0.72 |  | 63 | Bespoke - Phasing likely to be informed by scheme specific information, which currently assumes delivery within 5 years, as this pace is necessary to access affordable housing funding. Without an extant permission however this does seem optimistic. | [5 empty] | 0 | 0 | 0 | 0 | 31 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63
9 |  |  |  | 26 | 26 | 0 |  | 0 | 26 | Southfield | Acton |  |  |  |  | 0.63 |  | 26 | Scenario 28. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 26
10 |  |  |  | 112 | 18 | 94 |  | 0 | 18 | East Acton | Acton |  |  |  |  | 0.88 |  | 18 | Scenario 29. Pace of build out informed by gross figure. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 5 | 5 | 0 | 0 | 0 | 0 | 18
11 |  |  |  | 1228 | 998 | 230 |  | 998 | 0 | East Acton | Acton |  |  |  |  | 2.79 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 |  |  |  | 6501 | 6501 | 0 |  | 0 | 6501 | North Acton | Acton |  |  |  |  | 10.6 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  |  |  | 42 | 42 | 0 |  | 0 | 42 | North Acton | Acton |  |  |  |  | 0.2 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  |  |  | 419 | 377 | 42 |  | 0 | 377 | North Acton | Acton |  |  |  |  | 0.55 |  | 377 | Scenario 30 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 76 | 76 | 76 | 75 | 0 | 0 | 0 | 377
15 |  |  |  | 41 | 11 | 30 |  | 0 | 11 | North Acton | Acton |  |  |  |  | 0.3 |  | 11 | Bespoke - Phasing likely to be informed by scheme specific information (CFS feedback), which estimates delivery within 5 years. Without an extant permission however this does seem optimistic. Without further evidence revert to scenario 28. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 11
16 |  |  |  | 84 | 80 | -4 |  | -4 | 84 | Ealing Broadway | Ealing |  |  |  |  | 1.14 |  | 84 | Bespoke. Beyond 5 years | [5 empty] | 0 | 0 | 0 | 0 | 0 | 42 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84
17 |  |  |  | 443 | 443 | 0 |  | 0 | 443 | Ealing Broadway | Ealing |  |  |  |  | 3.59 |  | 443 | Beyond 5 years (new residential component). Scenario 30 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 88 | 89 | 89 | 89 | 0 | 0 | 0 | 443
18 |  |  |  | 220 | 216 | 4 |  | 173 | 43 | Ealing Broadway | Ealing |  |  |  |  | 0.64 |  | 43 | Phasing aligned with pending scheme - Scenario 15 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 43
19 |  |  |  | 79 | 77 | 2 |  | 0 | 77 | Ealing Broadway | Ealing |  |  |  |  | 0.71 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  |  |  | 22 | 22 | 0 |  | 0 | 22 | Ealing Broadway | Ealing |  |  |  |  | 0.08 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 |  |  |  | 80 | 80 | 0 |  | 0 | 80 | Ealing Broadway | Ealing |  |  |  |  | 0.18 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 |  |  |  | 62 | 62 | 0 |  | 0 | 62 | Ealing Broadway | Ealing |  |  |  |  | 0.17 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 |  |  |  | 9 | 9 | 0 |  | 9 | 0 | Ealing Broadway | Ealing |  |  |  |  | 0.2 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 |  |  |  | 90 | 90 | 0 |  | 0 | 90 | Walpole | Ealing |  |  |  |  | 2 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 |  |  |  | 188 | 188 | 0 |  | 0 | 188 | Ealing Broadway | Ealing |  |  |  |  | 1.2 |  | 188 | Beyond 5 years. Scenario 24. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 62 | 63 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188
26 |  |  |  | 146 | 142 | 4 |  | 0 | 142 | Walpole | Ealing |  |  |  |  | 0.86 |  | 142 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 29 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 36 | 36 | 0 | 0 | 0 | 0 | 142
27 |  |  |  | 33 | 33 | 0 |  | 0 | 33 | Walpole | Ealing |  |  |  |  | 0.47 |  | 33 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 28 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 33
28 |  |  |  | 116 | 110 | 6 |  | 0 | 110 | Ealing Broadway | Ealing |  |  |  |  | 1.03 |  | 110 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 29 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 27 | 28 | 28 | 0 | 0 | 0 | 0 | 110
29 |  |  |  | 29 | 29 | 0 |  | 29 | 0 | Walpole | Ealing |  |  |  |  | 0.07 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 |  |  |  | 46 | 33 | 13 |  | 0 | 33 | Walpole | Ealing |  |  |  |  | 0.24 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 |  |  |  | 94 | 76 | 18 |  | 0 | 76 | Hanwell Broadway | Ealing |  |  |  |  | 0.27 |  | 76 | Bespoke. Phasing to reflect extant permission on part of site. | [5 empty] | 0 | 0 | 0 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76
32 |  |  |  | N/A Covered in figure provided for 33 | N/A Covered in figure provided for 33 | N/A Covered in figure provided for 33 |  | N/A Covered in figure provided for 33 | N/A Covered in figure provided for 33 | Walpole | Ealing |  |  |  |  | 0.08 |  | N/A Covered in figure provided for EA18 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 |  |  |  | 526 | 468 | 58 |  | 0 | 468 | Walpole | Ealing |  |  |  |  | 0.89 |  | 468 | Scenario 31 (reflecting gross figure). | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 78 | 78 | 78 | 78 | 78 | 0 | 0 | 468
34 |  |  |  | 21 | 6 | 15 |  | NA | 0 | Hanwell Broadway | Ealing |  |  |  |  | 0.2 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 |  |  |  | 36 | 32 | 4 |  | 0 | 32 | Walpole | Ealing |  |  |  |  | 0.17 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 |  |  |  | 32 | 25 | 7 |  | 0 | 25 | Hanwell Broadway | Ealing |  |  |  |  | 0.16 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 |  |  |  | 21 | 21 | 0 |  | 0 | 0 | Walpole | Ealing |  |  |  |  | 0.17 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 |  |  |  | 396? (figure excludes 6a which is under construction) | 267? | 129? |  | 267? (figure excludes 6a which is under construction) | 0 | Hanwell Broadway | Ealing |  |  |  |  | 1.59 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 |  |  |  | 318 | 318 | 0 |  | 0 | 318 | Hanwell Broadway | Ealing |  |  |  |  | 1.49 |  | 318 | Bespoke - Whilst the capacity estimate here is not taken from an extant or pending permission, the site is subject to a live application at present. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 79 | 79 | 0 | 0 | 0 | 0 | 0 | 318
40 |  |  |  | 225 | 225 | 0 |  | 0 | 225 | Walpole | Ealing |  |  |  |  | 0.27 |  | 225 | Bespoke - Whilst the capacity estimate here is not taken from an extant or pending permission, the site is subject to a live application at present. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225
41 |  |  |  | 172 | 0 | 0 |  | 0 (Phase 2 - 172 lapsed) | 172 | Ealing Broadway | Ealing |  |  |  |  | 0.99 |  | 172 | Bespoke. Early CFS submission estimates delivery between years 6-10. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 57 | 57 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172
42 |  |  |  | 79 | 79 | 0 |  | 0 | 79 | Pitshanger | Ealing |  |  |  |  | 0.49 |  | 79 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 28 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 79
43 |  |  |  | 300 | 300 | 0 |  | 0 | 300 | Pitshanger | Ealing |  |  |  |  | 7.25 |  | 300 | Bespoke. Pre-app stage. | [5 empty] | 0 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300
44 |  |  |  | 19 | 13 | 6 |  | 0 | 13 | Pitshanger | Ealing |  |  |  |  | 0.35 |  | 13 | Beyond 5 years. Scenario 28 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 13
45 |  |  |  | 326 | 326 | 0 |  | 326 | 0 | Hanger Hill | Ealing |  |  |  |  | 5.39 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 |  |  |  | 97 | 97 | 0 |  | 0 | 97 | Hanger Hill | Ealing |  |  |  |  | 6.65 |  | 97 | Beyond 5 years. Figures not informed by extant or pending applications. Bespoke - whilst no recent pre-app interest the landowner is actively promoting site | [5 empty] | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97
47 |  |  |  | 142 | 142 | 0 |  | 0 | 142 | Hanger Hill | Ealing |  |  |  |  | 0.9 |  | 142 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 29 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 36 | 36 | 0 | 0 | 0 | 0 | 142
48 |  |  |  | 47 | 47 | 0 |  | 0 | 47 | Ealing Common | Ealing |  |  |  |  | 1.21 |  | 47 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 28 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 47
49 |  |  |  | 75 | 75 | 0 |  | 0 | 75 | Ealing Common | Ealing |  |  |  |  | 2.78 |  | 75 | Bespoke. Noting pre-app activity and modest expectations of the club delivery could occur at pace, although contingent on club finances. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
50 |  |  |  | 71 | 0 | 0 |  | 0 | 71 | Ealing Common | Ealing |  |  |  |  | 1.91 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 |  |  |  | 162 | 162 | 0 |  | 0 | 162 | Ealing Common | Ealing |  |  |  |  | 0.66 |  | 162 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 29 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 41 | 41 | 0 | 0 | 0 | 0 | 162
52 |  |  |  | 87 | 87 | 0 |  | 0 | 87 | Northfield | Ealing |  |  |  |  | 0.36 |  | 87 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 28 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 87
53 |  |  |  | 6 | 5 | 1 |  | 0 | 5 | Greenford Broadway | Greenford |  |  |  |  | 1.3 |  | 5 | Beyond 5 years | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
54 |  |  |  | 122 | 120 | 2 |  | 0 | 120 | Greenford Broadway | Greenford |  |  |  |  | 0.98 |  | 120 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 29 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 120
55 |  |  |  | 211 | 0 | 0 |  | 0 | 211 | Greenford Broadway | Greenford |  |  |  |  | 2.79 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 |  |  |  | 14 | 0 | 0 |  | 0 | 10 | Greenford Broadway | Greenford |  |  |  |  | 0.14 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 |  |  |  | 23 | 23 | 0 |  | 0 | 23 | Greenford Broadway | Greenford |  |  |  |  | 0.23 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 |  |  |  | 39 | 0 | 0 |  | 0 | 39 | Greenford Broadway | Greenford |  |  |  |  | 0.24 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 |  |  |  | 39 | 21 | 18 |  | 0 | 21 | Central Greenford | Greenford |  |  |  |  | 0.16 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 |  |  |  | 1139 | 1139 | 0 |  | 0 | 1139 | Central Greenford | Greenford |  |  |  |  | 4.21 |  | 1139 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 31 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189 | 190 | 190 | 190 | 190 | 190 | 0 | 0 | 1139
61 |  |  |  | 272 | 272 | 0 |  | 0 | 272 | Central Greenford | Greenford |  |  |  |  | 2.44 |  | 272 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 30 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 54 | 54 | 55 | 55 | 0 | 0 | 0 | 272
62 |  |  |  | 97 | 94 | 3 |  | 94 | 0 | Greenford Broadway | Greenford |  |  |  |  | 1.4 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 |  |  |  | 498 | 351 | 147 |  | 0 | 351 | Greenford Broadway | Greenford |  |  |  |  | 2.52 |  | 351 | Beyond 5 years. CfS submission suggests delivery within first 5 years, but in the absence of further evidence assign beyond 5 years. Bespoke | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 88 | 88 | 88 | 0 | 0 | 0 | 0 | 0 | 351
64 |  |  |  | 383 | 383 | 0 |  | 0 | 383 | Norwood Green | Hanwell |  |  |  |  | 1.44 |  | 383 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 30 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 76 | 77 | 77 | 77 | 0 | 0 | 0 | 383
65 |  |  |  | 23 | 23 | 0 |  | 0 | 23 | Hanwell Broadway | Hanwell |  |  |  |  | 0.17 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 |  |  |  | 37 | 37 | 0 |  | 0 | 37 | Hanwell Broadway | Hanwell |  |  |  |  | 0.17 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 |  |  |  | 23 | 14 | 9 |  | 0 | 14 | Hanwell Broadway | Hanwell |  |  |  |  | 0.24 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 |  |  |  | 16 | 16 | 0 |  | 0 | 16 | Hanwell Broadway | Hanwell |  |  |  |  | 0.22 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 |  |  |  | 159 | 157 | 2 |  | 0 | 157 | Hanwell Broadway | Hanwell |  |  |  |  | 0.83 |  | 157 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 29 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 39 | 39 | 40 | 0 | 0 | 0 | 0 | 157
70 |  |  |  | N/A Captured in figure provided for 69 | N/A Captured in figure provided for 69 | N/A Covered in figure provided for 69 |  | 0 | NA | Hanwell Broadway | Hanwell |  |  |  |  | 0.29 |  | N/A Covered in figure provided for HA06 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 |  |  |  | 23 | ? | ? |  | 0 | ? | Hanwell Broadway | Hanwell |  |  |  |  | 0.15 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 |  |  |  | 124 | 124 | 0 |  | 0 | 124 | Hanwell Broadway | Hanwell |  |  |  |  | 0.56 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 |  |  |  | 128 | 47 | 81 |  | 0 | 47 | Hanwell Broadway | Hanwell |  |  |  |  | 1.13 |  | 47 | Beyond 5 years. Scenario 29 (reflecting gross figure). | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 47
74 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | Hanwell Broadway | Hanwell |  |  |  |  | 1.91 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 |  |  |  | 700 | 347 | 353 |  | 0 | 347 | North Hanwell | Hanwell |  |  |  |  | 3.64 |  | 347 | Bespoke to reflect feasibility stage. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 69 | 69 | 69 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 347
76 |  |  |  | 505 | 241 | 264 |  | 241 | 0 | North Hanwell | Hanwell |  |  |  |  | 3.62 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 |  |  |  | 190 | 190 | 0 |  | 0 | 190 | Northolt Mandeville | Northolt |  |  |  |  | 0.95 |  | 190 | Bespoke to reflect feasibility stage. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 63 | 63 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190
78 |  |  |  | 106 | 106 | 0 |  | 106 | 0 | Northolt Mandeville | Northolt |  |  |  |  | 5.06 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 |  |  |  | 339 | 339 | 0 |  | 0 | 339 | Northolt Mandeville | Northolt |  |  |  |  | 5.54 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 |  |  |  | 632 | 209 | 423 |  | 0 | 209 | Northolt Mandeville | Northolt |  |  |  |  | 15.12 |  | 209 | Long term priority - 10 year plus. Scenario 31 (to reflect gross figure). | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 35 | 35 | 35 | 35 | 35 | 0 | 0 | 209
81 |  |  |  | 44 | 44 | 0 |  | 0 | 44 | Northolt Mandeville | Northolt |  |  |  |  | 0.29 |  | 44 | Bespoke to reflect recent pre-app interest, albeit end use may differ. | [5 empty] | 0 | 0 | 0 | 0 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44
82 |  |  |  | 212 | 212 | 0 |  | 0 | 212 | Northolt Mandeville | Northolt |  |  |  |  | 4.57 |  | 212 | Beyond 5 years. Scenario 29. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 53 | 53 | 53 | 0 | 0 | 0 | 0 | 212
83 |  |  |  | 61 | 0 | 0 |  | 0 | 61 | Northolt West End | Northolt |  |  |  |  | 0.52 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 |  |  |  | 235 | 197 | 38 |  | 0 | 197 | Northolt West End | Northolt |  |  |  |  | 4.85 |  | 197 | Bespoke. Longer term prospect - delivery anticipated beyond 10 years. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 49 | 49 | 50 | 0 | 0 | 197
85 |  |  |  | 262 | 107 | 155 |  | 0 | 107 | Northolt West End | Northolt |  |  |  |  | 11.35 |  | 107 | Bespoke. Delivery anticipated beyond 5 years. Some feasibility work has been undertaken. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 107
86 |  |  |  | 78 | 0 | 0 |  | 0 | 78 | Northolt West End | Northolt |  |  |  |  | 0.35 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 |  |  |  | 90 | 0 | 0 |  | 0 | 90 | Northolt West End | Northolt |  |  |  |  | 0.41 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 |  |  |  | 204 | 189 | 15 |  | 0 | 189 | Northolt West End | Northolt |  |  |  |  | 4.91 |  | 189 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 29. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 47 | 47 | 48 | 0 | 0 | 0 | 0 | 189
89 |  |  |  | 147 | 147 | 0 |  | 0 | 147 | Northolt West End | Northolt |  |  |  |  | 3.13 |  | 147 | Bespoke. Longer term prospect - delivery anticipated beyond 10 years. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 37 | 37 | 37 | 0 | 0 | 147
90 |  |  |  | 92 | 92 | 0 |  | 92 | 0 | Northolt Mandeville | Northolt |  |  |  |  | 0.43 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 |  |  |  | 0 | 0 | 0 |  | 0 | 6 | Northolt West End | Northolt |  |  |  |  | 0.39 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 |  |  |  | 98 | 98 | 0 |  | 0 | 98 | Perivale | Perivale |  |  |  |  | 0.31 |  | 98 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 28 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 98
93 |  |  |  | 48 | 48 | 0 |  | 0 | 48 | Perivale | Perivale |  |  |  |  | 0.16 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 |  |  |  | 47 | 47 | 0 |  | 0 | 47 | Perivale | Perivale |  |  |  |  | 0.4 |  | 47 | Beyond 5 years. Recent pre-app interest but for commercial only scheme. Scenario 28. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 47
95 |  |  |  | 190 | 190 | 0 |  | 0 | 190 | Perivale | Perivale |  |  |  |  | 1.87 |  | 190 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 29 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 47 | 48 | 48 | 0 | 0 | 0 | 0 | 190
96 |  |  |  | 505 | 505 | 0 |  | 0 | 505 | Southall Broadway | Southall |  |  |  |  | 1.22 |  | 505 | Bespoke. Early pre-app discussions with landowner. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 101 | 101 | 101 | 101 | 0 | 0 | 0 | 0 | 505
97 |  |  |  | 516 | 493 | 23 |  | 493 | 0 | Southall Broadway | Southall |  |  |  |  | 1.24 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 |  |  |  | 460 | 460 | 0 |  | 460 | 0 | Southall Broadway | Southall |  |  |  |  | 1.16 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 |  |  |  | 88 | 88 | 0 |  | 0 | 88 | Southall Broadway | Southall |  |  |  |  | 0.58 |  | 88 | Bespoke. Phasing to reflect extant permission and pre-app activity. | [5 empty] | 0 | 0 | 0 | 0 | 29 | 29 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88
100 |  |  |  | 103 | 103 | 0 |  | 0 | 103 | Southall Broadway | Southall |  |  |  |  | 1.18 |  | 103 | Bespoke. Note neighbouring site underpinned by 203705FUL has commenced. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 34 | 34 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103
101 |  |  |  | 148 | 142 | 6 |  | 0 | 142 | Southall Broadway | Southall |  |  |  |  | 1.04 |  | 142 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 29 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 36 | 36 | 0 | 0 | 0 | 0 | 142
102 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | Southall Broadway | Southall |  |  |  |  | 0.27 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 |  |  |  | 186 | 2 | 184 |  | 0 | 184 | Dormers Wells | Southall |  |  |  |  | 1.06 |  | 184 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 29 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 46 | 46 | 46 | 0 | 0 | 0 | 0 | 184
104 |  |  |  | 575 | 575 | 0 |  | 575 | 0 | Norwood Green | Southall |  |  |  |  | 0.61 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 |  |  |  | 457 | 439 | 18 (are these NSC?) |  | 95 | 344 | Norwood Green | Southall |  |  |  |  | 1.22 |  | 344 | Bespoke. Phasing to reflect existance of pending schemes on part of site. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 86 | 86 | 86 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 344
106 |  |  |  | 1274 | 1274 | 0 |  | 1395 | 0 | Norwood Green | Southall |  |  |  |  | 5 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 |  |  |  | 635 | 99 | 536 |  | 99 | 0 | Norwood Green | Southall |  |  |  |  | 13.48 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 |  |  |  | 453 | 448 | 5 |  | 448 | 0 | Southall Green | Southall |  |  |  |  | 2.05 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 |  |  |  | 3776 (5579 from original site) | 3776 (5579 from original site) | 0 |  | 0 (1803 from original site) | 3776 | Southall West | Southall |  |  |  |  | 22 |  | 3776 | Bespoke | [5 empty] | 0 | 0 | 0 | 0 | 0 | 377 | 377 | 377 | 377 | 378 | 378 | 378 | 378 | 378 | 378 | 3776
110 |  |  |  | 92 | 92 | 0 |  | 0 | 92 | Southall Green | Southall |  |  |  |  | 0.58 |  | 92 | Beyond 5 years. Figures not informed by extant or pending applications. Scenario 28 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 92
111 |  |  |  | 59 | 59 | 0 |  | 9 | 50 | Norwood Green | Southall |  |  |  |  | 0.68 |  | 50 | Bespoke. Beyond 5 years. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 16 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
112 |  |  |  | 55 | 12 | 43 |  | 0 | 43 | Norwood Green | Southall |  |  |  |  | 1.25 |  | 43 | Beyond 5 years. Scenario 28 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 43
113 |  |  |  | 42 | 42 | 0 |  | 0 | 42 | Norwood Green | Southall |  |  |  |  | 0.49 |  | 42 | Beyond 5 years. Scenario 28 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 42
114 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | Norwood Green | Southall |  |  |  |  | 24.67 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 |  |  |  | 64 | 60 | 4 |  | 0 | 60 | Norwood Green | Southall |  |  |  |  | 1.84 |  | 60 | Bespoke. Beyond 5 years. Some early pre-app discussions have occurred. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60
116 |  |  |  | 47 | 47 | 0 |  | 0 | 0 | Dormers Wells | Southall |  |  |  |  | 0.84 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 |  |  |  | 218 | 218 | 0 |  | 0 | 0 | Southall Broadway | Southall |  |  |  |  | 0.5 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 |  |  |  | 1463 | 945 | 518 |  | 0 | 945 | Dormers Wells | Southall |  |  |  |  | 10.03 |  | 945 | Note later phases may go beyond plan period | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 157 | 157 | 158 | 158 | 158 | 0 | 0 | 945
119 |  |  |  | 216 | 213 | 3 |  | 0 | 213 | Lady Margaret | Southall |  |  |  |  | 1.43 |  | 213 | Beyond 5 years. Scenario 29 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 53 | 53 | 54 | 0 | 0 | 0 | 0 | 213
120 |  |  |  | 546 | 545 | 1 |  | 0 | 0 | Southall West | Southall |  |  |  |  | 1.13 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 |  |  |  | 116 | 115 | 1 |  | 0 | 115 | Southall West | Southall |  |  |  |  | 0.17 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 |  |  |  | 614 | 415 | 199 |  | 0 | 415 | Norwood Green | Southall |  |  |  |  | 4.12 |  | 415 | Bespoke. CfS submission suggests delivery between years 5 to 10. Phasing also informed by gross figure. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 83 | 83 | 83 | 83 | 83 | 0 | 0 | 0 | 0 | 0 | 415
[20 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 537 | 1589 | 2009 | 3331 | 2870 | 2624 | 1969 | 1297 | 926 | 378 | 378 | 17908
0
0
Note on T4: Ian WEAKE: Timing of build out should have regard to the gross figures, specifically if net figure is small

## NSC Allocations
[25 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Site or Scheme ID | Site Allocation Ref. | Site Name / Address | Proposed Use | Bedrooms Gained | Bedrooms Lost | Net No. Bedrooms | NSC Type | Unit (C3) lost | Unit Gross (Converted) | Unit Net (Converted) | Overlapping Planning Permission | Net Capacity already assigned to pipeline or pending | Remaining Capacity not assigned to pipeline or pending | Ward | Neighbourhood Area | Easting | Northing | UPRN | Covered by existing Adopted Allocation | Site Area (ha) | Notes | Net Capacity to plug into Trajectory | Phasing Notes | Year of Trajectory | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | ? | None | 0 | 0 | Northolt West End | Northolt |  |  |  |  | 0.39 |  | 0 | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[24 empty] | Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acton
Ealing
Greenford
Hanwell
Northolt
Perivale
Southall

## Conv Windfall (Large Mplan)
[22 empty] | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Site or Scheme ID | Ref. | Site Name / Address | Proposed Use | Estimated Capacity Gross | Estimated Capacity Net | Existing Units | NSC Type | Unit Net (Converted) | Overlapping Planning Permission | Net Capacity already assigned to pipeline or pending | Remaining Capacity not assigned to pipeline or pending | Ward | Neighbourhood Area | Easting | Northing | UPRN | Site Area (ha) | Notes | Net Capacity to plug into Trajectory | Phasing Notes | Year of Trajectory | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Scheme Total
1 |  |  |  |  | 1752 | 0 |  |  |  |  | 1752 | South Acton | Acton | [5 empty] | 1752 | Beyond 5 years. Bespoke reflecting feasibility/masterplan stage. Capacity distributed over 10 years. | [5 empty] | 0 | 0 | 0 | 0 | 0 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 176 | 176 | 1752
2 |  |  |  |  | 119 | 0 |  |  |  |  | 119 | South Acton | Acton | [5 empty] | 119 | Scenario 34 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 24 | 24 | 24 | 24 | 0 | 0 | 119
3 |  |  |  |  | 319 | 0 |  |  |  |  | 319 | Hanger Hill | Ealing | [5 empty] | 319 | Scenario 35 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 46 | 46 | 46 | 46 | 319
4 |  |  |  |  | 153 | 0 |  |  |  |  | 153 | Hanwell Broadway | Hanwell | [5 empty] | 153 | Scenario 34 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 31 | 31 | 31 | 0 | 0 | 153
5 |  |  |  |  | 528 | 0 |  |  |  |  | 528 | Southall Green | Southall | [5 empty] | 528 | Scenario 36 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 76 | 76 | 76 | 528
6 |  |  |  |  | 79 | 0 |  |  |  |  | 79 | Southall Green | Southall | [5 empty] | 79 | Scenario 33 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 20 | 20 | 20 | 0 | 0 | 0 | 79
7 |  |  |  |  | 116 | 0 |  |  |  |  | 116 | Norwood Green | Southall | [5 empty] | 116 | Scenario 34 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 23 | 23 | 23 | 24 | 0 | 0 | 116
[21 empty] | Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 175 | 175 | 175 | 390 | 392 | 393 | 394 | 376 | 298 | 298 | 3066
0
0
0
0
0
0

## Conventional (Small Site)
| 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Year of Trajectory | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Small Site Input (net units) | 0 | 0 | 0 | 0 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 424

## Phasing Assumptions
|  |  | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | 2030-2031 | 2031-2032 | 2032-2033 | 2033-2034 | 2034-2035 | 2035-2036 | 2036-2037 | 2037-2038
Scenario | Status 1 - Planning | Status 2 - Scale | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Completions | Sites completed by 31 March 2023 | bar: 0
2 | Under Construction and prior approvals (full detailed permissions only) | Sites <10 new residential units under construction at 31 March 2023 | bar: 1
3 | Under Construction and prior approvals (full detailed permissions only) | Sites of 10-100 new residential units under construction at 31 March 2023 | bar: 1 to 2
4 | Under Construction and prior approvals (full detailed permissions only) | Sites of 100-250 new residential units under construction at 31 March 2023 | bar: 1 to 3
5 | Under Construction and prior approvals (full detailed permissions only) | Sites of 250-500 new residential units under construction at 31 March 2023 | bar: 1 to 4
6 | Under Construction and prior approvals (full detailed permissions only) | Sites of 500+ new residential units under construction at 31 March 2023 | bar: 1 to 5
7 | Full/detailed Planning Permission – not commenced | Sites <10 new residential units not started at 31 March 2023 | bar: 2
8 | Full/detailed Planning Permission – not commenced | Sites of 10-100 new residential units not started at 31 March 2023 | bar: 2 to 3
9 | Full/detailed Planning Permission – not commenced | Sites of 100-250 new residential units not started at 31 March 2023 | bar: 2 to 4
10 | Full/detailed Planning Permission – not commenced | Sites of 250-500 new residential units not started at 31 March 2023 | bar: 3 to 6
11 | Full/detailed Planning Permission – not commenced | Sites of 500+ new residential units not started at 31 March 2023 | bar: 3 to 7
12 | Outline Planning Permission or S106 pending (with resolution to grant) | Sites <10 new residential units not started at 31 March 2023 | bar: 5 to 6
13 | Outline Planning Permission or S106 pending (with resolution to grant) | Sites of 10-100 new residential units not started at 31 March 2023 | bar: 6 to 7
14 | Outline Planning Permission or S106 pending (with resolution to grant) | Sites of 100-250 new residential units not started at 31 March 2023 | bar: 6 to 8
15 | Outline Planning Permission or S106 pending (with resolution to grant) | Sites of 250-500 new residential units not started at 31 March 2023 | bar: 6 to 9
16 | Outline Planning Permission or S106 pending (with resolution to grant) | Sites of 500+ new residential units not started at 31 March 2023 | bar: 6 to 10
17 | Pending consideration (i.e. without resolution to grant) | Sites <10 new residential units not started at 31 March 2023 | bar: 6
18 | Pending consideration (i.e. without resolution to grant) | Sites of 10-100 new residential units not started at 31 March 2023 | bar: 6 to 7
19 | Pending consideration (i.e. without resolution to grant) | Sites of 100-250 new residential units not started at 31 March 2023 | bar: 6 to 8
20 | Pending consideration (i.e. without resolution to grant) | Sites of 250-500 new residential units not started at 31 March 2023 | bar: 7 to 10
21 | Pending consideration (i.e. without resolution to grant) | Sites of 500+ new residential units not started at 31 March 2023 | bar: 7 to 11
22 | Pre-application interest only | Sites <10 new residential units not started at 31 March 2023 | bar: 6 to 7
23 | Pre-application interest only | Sites of 10-100 new residential units not started at 31 March 2023 | bar: 6 to 8
24 | Pre-application interest only | Sites of 100-250 new residential units not started at 31 March 2023 | bar: 6 to 8
25 | Pre-application interest only | Sites of 250-500 new residential units not started at 31 March 2023 | bar: 7 to 10
26 | Pre-application interest only | Sites of 500+ new residential units not started at 31 March 2023 | bar: 7 to 11
27 | No planning activity/interest of note | Sites <10 new residential units not started at 31 March 2023 | bar: 7 to 8
28 | No planning activity/interest of note | Sites of 10-100 new residential units not started at 31 March 2023 | bar: 7 to 9
29 | No planning activity/interest of note | Sites of 100-250 new residential units not started at 31 March 2023 | bar: 8 to 11
30 | No planning activity/interest of note | Sites of 250-500 new residential units not started at 31 March 2023 | bar: 8 to 12
31 | No planning activity/interest of note | Sites of 500+ new residential units not started at 31 March 2023 | bar: 8 to 13
32 | Windfall Large | Sites/Areas yielding <10 new residential units not started at 31 March 2023 | bar: 9 to 12
33 | Windfall Large | Sites/Areas yielding 10-100 new residential units not started at 31 March 2023 | bar: 9 to 12
34 | Windfall Large | Sites/Areas yielding 100-250 new residential units not started at 31 March 2023 | bar: 9 to 13
35 | Windfall Large | Sites/Areas yielding 250-500 new residential units not started at 31 March 2023 | bar: 9 to 15
36 | Windfall Large | Sites/Areas yielding 500+ new residential units not started at 31 March 2023 | bar: 9 to 15

## Capacity Tool Template
Site Name
[25 empty] | Residential - Density key (GLA Design Guidance) | [9 empty] | Non-residential - Density key (GLA Design Guidance)
Step 1 - Total GIA | Type of development | Total site size (sqm) | Developable area (sqm) | Building footprint/site coverage (sqm) | Prevailing Height (storeys) | Total GEA (sqm) | Total GIA (sqm) | [17 empty] | Town centres |  | >200d/ha size) | [7 empty] | Town centres |  | >2.0
[25 empty] | Urban neighbourhoods |  | 60-120d/ha | [7 empty] | Urban neighbourhoods |  | >1.0
[25 empty] | Suburbs |  | 30-50 d/ha | [7 empty] | Suburbs |  | >0.5
| Residential uses |  |  | Non-residential uses | [5 empty] | Residential - Typologies | [14 empty] | Residential - Density checker |  |  |  | Non-residential - Typologies | [5 empty] | Mixed-use - Density checker (as Plot Ratio/Floor-to-Area Ratio)
Step 2A - Mix of Uses | Flats | Houses | Total residential (% split) | Office | Retail | Light industry | Other use 1 | Other use 2 | Total non-residential uses (% split) | Step 2B - Split of Uses | Residential Total | Residential Total | Flats | [6 empty] | Houses |  |  |  |  | Site area (hectares) | Total no. of resi units | PTAL rating | Total density (unit/ha) | Total amount of Non-residential floorspace | Office | Retail | Light industry | Other use 1 | Other use 2 | Typology/setting (Allies & Morrison) | Associated Proposed Floor to Area Ratio for typology/setting | Indicative new plot ratio
| % | % | % | % | % | % | % | % | % |  | Indicative Gross GIA (sqm) | Indicative Gross NIA (sqm) | Indicative Gross GIA for flats (sqm) | Indicative Gross NIA for flats (sqm) | No. of 1-Bed Flats @ 50sqm | No. of 2-Bed Flats @ 70sqm | No. 3-Bed Flats @ 86sqm | Air space modifier for <4st. Flat blocks | Total no. of flats | Indicative Gross GIA for houses (sqm) | Indicative Gross NIA for houses (sqm) | No. of 3-Bed Houses @ 96sqm | No. of 4-Bed Houses @ 113.5sqm | Total no. of houses |  |  |  |  | Indicative Gross GIA m2 | Indicative Gross GIA m2 | Indicative Gross GIA m2 | Indicative Gross GIA m2 | Indicative Gross GIA m2 | Indicative Gross GIA m2 |  |  | Plot Ratio (Site area vs. Building coverage)
| 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #DIV/0!
[11 empty] | Target accommo mix (%) |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| Residential units |  |  | Non-residential | [8 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Step 3 - Gross to Net capacity | No. of existing residential units | No. of proposed residential units | Total net gain of residential units | Amount of existing non-resi floorspace (GEA as sqm) |  | Amount of proposed non-resi floorspace (GIA as sqm) |  | Total net gain of non-resi floorspace (GIA sqm)
|  | 0 | 0 | 0 |  | 0 |  | 0