2011 Children and Young People Plan Timeline

Version 2.  April 2010 – will be subject to revision

| Action/decision | Responsible Officer /Grouping | Due Date |
| --- | --- | --- |
| Consultation: CYPP Development Day | MP | 26 Feb 10 |
| Consultation: CSMT extended group | MP | 4 March 10 |
| Draft revised Priorities from Children’s Trust CYPP Development event circulated | MP | 5 March 10 |
| Draft timeline to Joint Performance Management Group | SH | 4 March 10 |
| Draft Project Plan completed | SH/MU | 9 April 10 |
| Consultation: Timeline and input from schools Children’s Trust Consultative group on revised priorities | MP | 25 March 10 |
| Revise timeline and briefing in response to new guidance issues 03 2010 | SH/MU | 31 March 10 |
| CYPP core 2010 data set received | SH | 1 April 10 |
| Draft communication / consultation plan completed | MU/EC | 22 April 10 |
| Consultation: Children’s Trust Operational Board Local Strategic Partnership Board | MP MP | 20 Apr 10 tba |
| Data: JSAN data collection project completed for phase 1 | MU | 22 Apr 10 |
| Data : JSNA data analysis priorities agreed based upon draft CYPP priorities | CYPP group | May 2010 |
| Consultation: LA/ Quadrant Heads Group | MP | 11 May 10 |
| Consultation : 14-19 Partnership Group | MP | 12 May 10 |
| Consultation: Chairs of Governors and Head Teachers meeting | MP | 13 May 10 |
| Consultation: Children’s Trust Operations Board – JSNA priorities | JF/MU | 18 May 10 |
| CYPP 2010/11 refresh published | Children’s Trust | June 2010 |
| Needs Assessment based upon data and customer consultation undertaken | CYPP group | May 2010 – October 2010 |
| Priorities revised and reviewed based upon Needs Assessment outcomes, Plan drafting | CYPP stakeholders | November 2010 – December 2010 |
| Consultation: draft plan out for consultation | CYPP group Children’s Trust | January - February 2011 |
| Plan finalised and stakeholder sign off agreed | Children’s Trust | March 2011 |
| Published |  | April 2011 |

Initials

MP = Marcella Phelan

MU= Mary Umrigar

SH= Sue Hunter

MPI= Meri Pesola

WC=Wai Chan

2011 Children and Young People Plan Timeline

Version 2 April 2010 –  will be subject to revision