## LIS Project Plan
Data collection and sharing outline draft project plan
the following timetable provides an overview of the potential timeline for a project that resulted in the development of a LIS procured externally
the viability of this as a solution will be tested as part of initial stages of the project, but is represented as the potentially longest duration of the project
procurement timescales and requirements will need to be confirmed further as the feasibility of this route is confirmed -
dates relating to procurement and implementation are provisional and indicative at this stage
Overview |  |  |  | Planning | [9 empty] | Implementation
WorkStream | Stage | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01
System | Scoping | 2011-06-01: Partner discussions around system specification and viability of technological solution; 2011-07-01: Consider market for supply and potential opportunities; 2011-08-01: Consultation on requirements with partners; 2011-09-01: Finalise requirements
| Procurement | 2011-09-01: Issue Pre Qualification Questionnaire (PQQ); 2011-10-01: Deadline for submissions of interest; 2011-11-01: Issue of the invitation to tender (ITT); 2011-12-01: Suppliers to submit responses; 2012-01-01: LSP Executive to award contract
| Implementation | 2012-02-01: Install system; 2012-03-01: System testing; 2012-05-01: Finalise applications and open web portal.; 2012-06-01: Launch System for Partnership usage; 2012-09-01: Launch System for public usage
Data | Assessment | 2011-02-01: Audit of current of all current existing partner information, where held, how held, how collected and format; 2012-07-01: Analysis of system usage and uptake
| Management | 2011-05-01: Mapping of data and reporting mechanisms - how data is analysed and used. Short term efficiencies delivered.; 2012-03-01: Upload existing data (where applicable).; 2012-05-01: Continuous updating of system data.
Governance | Communications and Engagement | 2011-02-01: Liasion with data managers from across partnership to access information, understand perspectives and develop future solutions; 2011-12-01: Develop LIS Communications plan; 2012-06-01: Roll out communications plan
| Training | 2012-06-01: Support and training offered to partners (where applicable) .